## Sheet1
Example Project Plan Template
Task | Person Responsible | Resources needed | Complete by
|  |  | 2022 | [11 empty] | 2023
|  |  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Planning ahead
Compile a contact list of everyone that can help out with the plan | ED | Volunteer time | bar: 2022 Mar
Secure Parish Council sponsorship | ED | Volunteer time | bar: 2022 Mar
Organise social event to raise additional funds | ED | Hire of village hall, refreshments | bar: 2022 Apr to 2022 May
Understanding your Community
Research local history | VH | Volunteer time | bar: 2022 Apr to 2022 May
Research local statistics | VH | Volunteer time | bar: 2022 Apr to 2022 May
Contact SCDC to find out if any existing Community-led plans already exist for the area | VH | Volunteer time | bar: 2022 Apr to 2022 May
Create discussion forum on Parish Council website | VH | Volunteer time | bar: 2022 Jun to 2022 July
Create a wall for people to write ideas on | VH | Pens and Post-it notes, Volunteer time | bar: 2022 Jun to 2022 July
Design questionnaire and send (electronically or paper form) to all households, businesses and organisations | VH | Printing of questionnaire (x 1000) and put electronic version on Village website and social media | bar: 2022 Jun to 2022 July
Prioritising and planning action
Collate and analyse results from the consultation | ED | Volunteer time | bar: 2022 Aug to 2022 Sep
Publish results of the consultation in the Village newsletter and on parish council website | ED | Cost of sumbmiting article, volunteeer time | bar: 2022 Oct
Hold open meeting for people to discuss and vote on ideas for action | ED | Hire of village hall, refreshments, advertise event | bar: 2022 Nov
Drafting the plan
Draft plan, to include what the plan is about, evidence of local needs and priorities and action plan | ED | Printing of draft plan (x 100), Volunteer time | bar: 2022 Dec to 2023 Feb
Send draft to members of the community and interested organisations for comment | ED | Volunteer time | bar: 2023 Mar to 2023 May
Make changes to draft based on comments | ED | Volunteer time | bar: 2023 Jun
Finalising the plan
Make sure the plan is in a format that can be read, but not changed by readers | ED | Volunteer time
Hold a public event to launch the plan e.g a celebration of achievements to date | ED | Hire of village hall, refreshments
Implement and monitor the plan
Put plan into action | ED | Volunteer time
Revisit the action plan on a regular basis to make sure everyone is clear about what needs to be done | ED | Volunteer time