South Cambridgeshire Community Safety Partnership

Operational Plan 2019/20/21

The Community Safety Partnership is responsible for improving community safety, including reducing crime, disorder, substance misuse and reoffending in South Cambridgeshire. The partnership includes the local authorities, police, fire service, NHS, probation service, community rehabilitation company and the voluntary sector. We work alongside the Police and Crime Commissioner.

Through our two-year Operational Plan we will:

1. Support vulnerable groups
2. Tackle thefts from homes and cars
3. Build resilient communities

As a partnership all our actions try to add value to what we can do individually as organisations. We do not list everything we do separately. We also have a two-year Transformation Plan that should be viewed alongside this one.

The Community Safety Partnership Board meets twice a year to provide direction and oversight. The Tasking and Coordination Group meets monthly to make sure that the partnership’s plans are delivered.

# Summary Action Plan

|  |  |  |  |
| --- | --- | --- | --- |
| **Action** | **Lead Team, Organisation** | **Resources** | **Timescales (complete by)** |
| Coordinate agency responses to local issues (Problem Solving Group) | Environmental Health, South Cambridgeshire District Council | * Staff time | Monthly, ongoing |
| Coordinate, manage and participate in the Community Trigger process | Environmental Health, South Cambridgeshire District Council | * Staff time | Ongoing, as required |
| Domestic Homicide Reviews:   * Support and facilitate the completion of two Domestic Homicide Reviews * Commission further reviews as required | Sustainable Communities and Wellbeing Service, South Cambridgeshire District Council | * Pooled funding (allocated) * Staff time | HO guidance states within 6 months. This is rarely possible, and permission is sought, and granted to extend timescales as a matter of course.  DHR 1 – at action planning stage  DHR 2 – at report-writing stage |
| Hoarding Project to tackle the causes of hoarding behaviours:   * Confirm project * Carry out and evaluate project | Environmental Health, South Cambridgeshire District Council | * OPCC Funding (allocated) * Staff time | Seek OPCC permission to carry forward and use grant funding underspend – Dec 2019  Define Project – Jan 2020  Deliver Project – Feb-May 2020  Evaluate – June 2020 |
| Communicate with local communities so they can recognise and report incidents or concerns about:   * Domestic abuse * Violence against women and girls * Cyber harassment, particularly young people focussed * Scams and rogue trading * Radicalisation * Hoarding * Hate crime * Modern Slavery | Sustainable Communities and Wellbeing Service, South Cambridgeshire District Council | * Staff time | In accordance with CSP comms plan. Ongoing as appropriate. |
| Host at least one ‘Community Safety Event’ annually to engage with local people | Sustainable Communities and Wellbeing Service, South Cambridgeshire District Council | * Staff time * £500 for venue, refreshments, printing etc (Pooled Fund) | Next event, March 2020 |