## Sheet1
Example Action Plan Template
Issue | Specific issue | Example project | Outcome sought | Priority | Action | Action Start Date | Action completion date | Person or organisation responsible | Resources needed | Expected project completion date
Social
Post Covid specific | Loneliness and Isolation since Covid | Set up a Community café | Reduction in loneliness and isolation | High | Investigate suitable venues | Soon |  | Local Timebanking coordinator | Hire of village hall, volunteer time and donations of cakes/tea/coffee etc | Spring 2022
[5 empty] | Book venue | 2022-01-01
[5 empty] | Recruit volunteers to help | 2022-01-01
[5 empty] | Publicise in village magazine and on social media | 2021-12-01
Health and Wellbeing | Lack of indoor keep fit classes | Keep Fit/Yoga classes at Village hall | Improvement in physical and mental health | Medium | Contact local instructors | 2022-03-01 |  | Parish Council | Parish Clerk Time. Costs to be ascertained | Autumn 2022
[5 empty] | Contact leah.collis@scambs.gov.uk (South Cambridgeshire District Council) | 2022-04-01
[5 empty] | Investigate suitable venues | 2022-04-01
[5 empty] | Book venue | 2022-04-01
[5 empty] | Publicise in village magazine and social media | 2022-04-01
| Mental Health issues increasing | Mental Health Awareness training | Improvement in mental health | Medium | Contact the Christian Safeguarding Services (thecss.co.uk) and Talking FreeEly - https://en-gb.facebook.com/TalkingFreELY/about/ who provide Mental Health and Awareness Training courses | 2022-04-01 |  | Parish Council | Parish Clerk Time. Costs to be ascertained | Autumn 2022
Housing | Young people having difficulty in getting onto the housing ladder locally | Young People's Housing | To provide young people with the opportunity to purchase their own homes | Low | Explore the possibility of undertaking a Neighbourhood Plan to incorporate a proportion of housing for young people | Summer 2021 |  | Parish Council | None | Spring 2022
Community Safety | Speeding in High St | Setting up of a Community speedwatch scheme | Reduction in speeding | High | Identify volunteers from the village (approx. 9 volunteers) | ASAP |  | Parish Council & Community volunteers | Volunteer time | Autumn 2022
[5 empty] | Contact Cambridgeshire Constabulary | ASAP
[5 empty] | Volunteer training | By summer 2022
[5 empty] | Decide and coordinate speed watch days/hours | Autumn 2022
| Increase in vehicle crime and bike thefts | Setting up of a Community Safety group | Reduced Crime and Antisocial behaviour | High | Investigate what is required to set up a community safety group | 2022-01-01 |  | Parish Council clerk | Volunteer time | Autumn 2022
[5 empty] | Contact South Cambridgeshire District Council | 2022-01-01
Sport, Recreation and Arts | Tennis club cannot play in winter evenings | Floodlighting for the Tennis Club | Provision of floodlights to tennis courts | Medium | Tennis Club to carry out a feasibility study on the provision of floodlighting to tennis courts. | 2022-02-01 |  | Tennis Club | Cost of installation circa £15,000 (may be less if grant funding secured). | Autumn 2023
[5 empty] | Contact Lawn Tennis Association for advice | 2022-02-01
[5 empty] | Obtain quotes for the work | 2022-02-01
[5 empty] | Investigate and apply for grant funding | 2022-03-01
[5 empty] | Installation of floodlights | Summer 2022
Community Facilities (Public and private) | Additional seating needed at park | Park bench project | Memorial bench installed | Medium | Identify a site | 2022-12-01 |  | Parish Council Clerk | Clerk time. Cost of bench and installation is provided by a family member | Spring 2023
[5 empty] | Identify a supplier and installer | 2022-12-01
[5 empty] | Identify a company to provide future maintenance | 2023-01-01
Community Assets | Village would like the local pub to reopen | Community ownership of pub | Pub re-opened in Village | Low | Contact South Cambridgeshire District Council | Spring 2021 |  | Local Residents Association | Volunteer time | Summer 2023
Community services | Support required to help older people to live independently in their homes | Village Mobile Warden Scheme | Allows people to live independently in their own home. Reduction in loneliness and social isolation | High | Contact South Cambridgeshire District Council: duty.communities@scambs.gov.uk for further advice. Also contact Age UK: wardens@ageukcap.org.uk | 2021-12-01 |  | Parish Council Clerk | Clerk time | Spring 2022
|  | Good Neighbour Scheme |  | High | Contact Care Network to find out about the Good Neighbour schemes. | 2021-12-01 |  | Parish Council Clerk | Clerk time | Spring 2022
Faith-based activities | Not enough being done to welcome newcomers to the village | Newcomer project | Develop inclusivity to new members of the community | Medium | Promotion via social media and Parish magazine | 2022-01-01 |  | Members of Church | £100 for paper and printing and people’s time | Spring 2022
[5 empty] | Design and print information packs | 2022-01-01
[5 empty] | Organise welcome mornings | 2022-01-01
Children and Young people | Lack of engagement with the younger generation in village | What do young people want? | Young people have a voice on parish matters | High | Parish Council and Education Youth Worker to meet with young people and establish a framework for operation e.g. A Parish Council youth forum or activities for young people | Immediate with aim to set up in 6 to 9 months |  | Parish Council, Community Education detached youth worker. Editor of the Village magazine | £500 per year from Parish Council | Spring 2022
Elderly Support | Provide a community transport scheme for those unable to drive | Project Community Transport | Making it easier for the elderly to get about | High | Investigate numbers of elderly people requiring this service | Summer 2022 |  | Parish Council | Clerk’s time | Winter 2022
[5 empty] | Research options available and seek advice and from South Cambridgeshire District Council | Summer 2022
[5 empty] | Promotion via social media and Parish magazine | Autumn 2022
[5 empty] | Launch the service | Autumn 2022
Environment
Green Issues | Not enough trees in Village | Six Free Trees | More trees planted to reduce carbon emissions and increase biodiversity | Immediate | Identify suitable areas on parish council land for tree planting | 2021-10-01 |  | Parish Council | Time to plan trees | 2021-12-01
[5 empty] | Apply for Six Free Trees from South Cambridgeshire District Council | End oct 2021
[5 empty] | Plant trees | 2021-12-01
Parish Emergency/Flood Planning | Potential issue if emergency services are delayed and a community response is not in place to respond to an emergency | Project parish emergency/flood planning | Village better equipped to deal with emergency situations such as flooding | High | Learn about parish emergency planning | As soon as possible |  | Parish council | Help from South Cambridgeshire District Council and time taken | Summer 2022
[5 empty] | Contact South Cambridgeshire District Council for flood planning advice | As soon as possible
[5 empty] | Create an Emergency Plan Committee/ Working Group – key people in your community who will represent it in an emergency | As soon as possible
[5 empty] | Fill out the SCDC Parish Emergency Plan Template | As soon as possible
[5 empty] | Identify and recruit for volunteers for the key components of the emergency plan: | As soon as possible
[5 empty] | Identify communal places of safety for evacuation | As soon as possible
Transport, Travel and Access | Re-routing of evening bus needed | Evening bus service | evening bus service set up | High | Contact bus company to ask to include the village on the current evening service visiting the next nearest village. | within 6 months |  | Parish Council Chair | Parish Council Chair time | Summer 2022
Highways and Footpaths | Speeding in High St | Setting up of a Community speedwatch scheme | Reduction in speeding | High | Identify volunteers from the village (approx 9 volunteers) | ASAP |  | Parish Council & Community volunteers | Volunteer time | Autumn 2022
[5 empty] | Contact Cambridgeshire Constabulary | ASAP
[5 empty] | Volunteer training | By summer 2022
[5 empty] | Decide and coordinate speedwatch days/hours | Autumn 2022
Recycling and Litter | Not enough being done to tackle climate change | Set up of a recycling point in the village | Increase in recycling, lowering in carbon emissions | High | Engage with local community to see if anyone would like to take on the role of Recycling Champion | ASAP |  | Local environmental group | Volunteer time | Spring 2022
[5 empty] | Contact South Cambridgeshire District Council to see if a recycling point can be set up | ASAP
| Litter becoming a problem in the Village | Community Litter pick | Reduction in litter |  | More information can be found from South Cambridgeshire District Council | ASAP
[5 empty] | Recruit Volunteers and publicise | ASAP
Economic
Digital Connectivity | Complaints from local businesses and residents about poor mobile phone signal and broadband coverage | Connectivity project | Better Connectivity in village | Medium | Survey village and local businesses to identify extent of need | 2022-04-01 |  | Parish Council Clerk | Clerk’s time | Autumn 2022
[5 empty] | Contact Connecting Cambridgeshire who help deliver the digital infrastructure for Cambridgeshire and Peterborough | 2022-04-01
Business | Local businesses struggling | Market Project | To encourage people to buy locally | Medium | Identify a location within the Village | 2022-04-01 |  | Parish Council Clerk | Clerk’s time | Autumn 2022
[5 empty] | Compile a list of interested businesses | 2022-04-01
[5 empty] | Contact South Cambridgeshire District Council for advice | 2022-04-01
Employment | High unemployment in village | Job Club project | Higher levels of employment, improvement in mental health | High | Explore possibility of setting up a job club at local library | 2022-03-01 |  | Local library, Parish council | Volunteer time | 2023-04-01
[5 empty] | Signpost unemployed to volunteering opportunities | 2022-03-01
|  | Financial and employment advice for those on low Income | improvement in mental health | High | Signpost those on low incomes to benefits | 2022-03-01
[5 empty] | Contact Citizens advice for leaflets | 2022-03-01
|  | Shared work space project | improvement in mental health |  | Identify options for shared working spaces for those unable to work from home | 2022-03-01
Education | Evening classes required | Adult Education project | Improvement in mental health and acquisition of new skills | Low-med | Speak to local school to see if they can provide evening classes | Winter 2022 |  | Local library, Parish council | Volunteer time | Autumn 2024
[5 empty] | Contact Cambridgeshire Skills for advice on Cambsals@cambridgeshire.gov.uk, or by calling 01353 613013. | Winter 2022